## Test Criteria
Items to be tested
Test Case # | Item to Test | Test Description | Test Date | Responsibility
1 | AC-7 | Unsuccessful Login Attempts | 2020-11-20 | Greg Eure
2 | AU-2 | Audit Events | 2020-11-20 | Greg Eure
3 | CM-10 | Software Usage Restrictions | 2020-11-21 | Greg Eure
4 | IA-6 | Authenticator Feedback | 2020-11-21 | Greg Eure
5 | SA-2 | Allocation of Resources | 2020-11-21 | Greg Eure
6 | SC-5 | Denial of Service Protection | 2020-11-21 | Greg Eure
7 | SI-3 | Malicious Code Protection | 2020-11-21 | Greg Eure
8 | AC-2 | Account Management | 2020-11-21 | Muhammad Zahid
9 | AC-5 | Separation of Duties | 2020-11-21 | Muhammad Zahid
10 | AT-3 | Role-Based Security Training | 2020-11-21 | Muhammad Zahid
11 | AU-3 | Content of Audit Records | 2020-11-21 | Muhammad Zahid
12 | CM-6 | Configuration Settings | 2020-11-22 | Muhammad Zahid
13 | AU-8 | Time Stamp | 2020-11-22 | Muhammad Zahid
14 | AC-8 | System Use Notification | 2020-11-22 | Muhammad Zahid
15 | AC-14 | Permitted Actions Without Identification or Authentication | 2020-11-22 | Estefania Lopez
16 | AC-17 | Remote Access | 2020-11-22 | Estefania Lopez
17 | AC-22 | Publicly Accessible Content | 2020-11-22 | Estefania Lopez
18 | SA-3 | System Development Life Cycle | 2020-11-25 | Estefania Lopez
19 | IR-4 | Incident Handling | 2020-11-23 | Estefania Lopez
20 | SC-7 | Boundary Protection | 2020-11-23 | Estefania Lopez
21 | AC-3 | Access Enforcement | 2020-11-23 | Estefania Lopez
22 | PE-15 | Water Damage Protection | 2020-11-23 | Calvin Ton
23 | CA-5 | Plan of Action and Milestones | 2020-11-23 | Calvin Ton
24 | CP-9 | Information System Backup | 2020-11-23 | Calvin Ton
25 | CP-10 | Information System Recovery and Reconstitution | 2020-11-23 | Calvin Ton
26 | CM-2 | Baseline Configuration | 2020-11-24 | Calvin Ton
27 | MP-2 | Media Access | 2020-11-24 | Calvin Ton
28 | PE-8 | Visitor Access Records | 2020-11-24 | Calvin Ton
29 | AC-20 | Use of External Information Systems | 2020-11-24 | Junyan Liu
30 | AT-4 | Security Training Record | 2020-11-24 | Junyan Liu
31 | CM-11 | User-Installed Software | 2020-11-24 | Junyan Liu
32 | IR-5 | Incident Monitoring | 2020-11-24 | Junyan Liu
33 | PS-7 | Third-Party Personnel Security | 2020-11-24 | Junyan Liu
34 | PS-6 | Access Agreements | 2020-11-24 | Junyan Liu
35 | PL-4 | Rules of Behavior | 2020-11-24 | Junyan Liu
36 | PE-13 | Fire Protection | 2020-11-25 | Muhammad Zahid
Test Approach(s)
Our testing approach was to follow the test case steps exactly, using the methods of INSPECT, TEST, OBSERVATION, and ANALYSIS, incorporate any test data, and then observe and document the results for each testing step. For any test cases where organizational document inspection was required, these were generally not available to be implemented.
Test Regulatory / Mandate Criteria
The system was tested using the 35 NIST 800-53 (Rev. 4) low-impact controls listed above
Test Pass / Fail Criteria
If the output of the command or step taken to test our database is as expected then we consider that a pass, if the output is not what we expected it is a fail.
Test Entry / Exit Criteria
Test case and any application and/or control documentation is available, and all prerequisite conditions are met. The exit criteria was different for every test but generally it was when we had enough data to pass the NIST control testing.
Test Deliverables
For each test we have filled out a form that includes the test case description, tester's name, date tested, prerequisties, steps, expected results, actual results, and whether the test passed, failed, was not executed, or was suspended.
Test Suspension / Resumption Criteria
Component testing will be suspended under the following conditions: critical error(s) found preventing test completion, change of business requirements, or change of environment components or technology including different version. Component testing will resume when the following criteria are met: all issues in suspension criteria have been resolved or mitigated.
Test Environmental / Staffing / Training Needs
In order to perform testing we needed to install a server running Ubuntu, install MySQL and MySQL Workbench, and import the GlobalProj database. Test users need to have a general understanding and proficiency with linux, and the mysql command-line, and limited understanding of MySQL Workbench.

## Test Case 1
Test Case ID |  | 1 | Test Case Description | Unsuccessful login attempts account lockout for 1 day after 3 invalid attempts
Created By |  | Greg Eure | Reviewed By | Greg Eure |  | Version |  | 1
QA Tester’s Log |  | Test case passed
Tester's Name |  | Greg Eure | Date Tested | 2020-11-20 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data
1 | Access to MySQL Server O/S via terminal or ssh |  |  | 1 | userid = testuser
2 | Account defined on O/S allowing remote login |  |  | 2 | password = pAssw0rD
3 | Account defined on MySQL database server
4 | Account configured for FAILED_LOGIN_ATTEMPTS=3 and PASSWORD_LOCK_TIME=1
Test Scenario | Verify that account locks after entering wrong password 3 times
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | [TEST] Go to a command shell on the server where MySQL is installed. |  | Command shell should open | As expected |  |  | Pass
2 | [TEST] Enter 'mysql -u testuser -p' |  | Should be prompted for password | As expected |  |  | Pass
3 | [TEST] Enter an incorrect password |  | Access Denied | As expected |  |  | Pass
4 | [TEST] Enter 'mysql -u testuser -p' |  | Should be prompted for password | As expected |  |  | Pass
5 | [TEST] Enter an incorrect password |  | Access Denied | As expected |  |  | Pass
6 | [TEST] Enter 'mysql -u testuser -p' |  | Should be prompted for password | As expected |  |  | Pass
7 | [TEST] Enter an incorrect password |  | Access Denied; Account is blocked for 1 day due to 3 consecutive failed logins | As expected |  |  | Pass

## Test Case 2
Test Case ID |  | 2 | Test Case Description | Database access attempts cause event to be logged (auditing)
Created By |  | Greg Eure | Reviewed By | Greg Eure |  | Version |  | 1
QA Tester’s Log |  | Test case passed
Tester's Name |  | Greg Eure | Date Tested | 2020-11-20 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data
1 | Access to MySQL Server O/S via terminal or ssh |  |  | 1 | userid = testuser
2 | Account defined on O/S allowing remote login |  |  | 2 | password = pAssw0rD
3 | Account defined on MySQL database server
4 | MySQL Server configured according to NIST AU-2 Control Document
Test Scenario | Verify that audit is functioning and logging events
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | [TEST] Go to a command shell on the server where MySQL is installed. |  | Command shell should open | As expected |  |  | Pass
2 | [TEST] Enter 'mysql -u testuser -p' |  | Should be prompted for password | As expected |  |  | Pass
3 | [TEST] Enter 'use GroupProj;' |  | Database changed' | As expected |  |  | Pass
4 | [TEST] Enter 'select * from GroupProj.Angola;' |  | 7 rows in set (0.00 sec) | As expected |  |  | Pass
5 | [TEST] Enter sudo cat /var/log/mysql/audit.log |  | <AUDIT_RECORD NAME="Query" RECORD="69_2020-11-21T01:59:59" TIMESTAMP="2020-11-21T02:12:05Z" COMMAND_CLASS="select" CONNECTION_ID="8" STATUS="0" SQLTEXT="select * from GroupProj.Angola" USER="root[root] @ localhost []" HOST="localhost" OS_USER="" IP="" DB="" /> | As expected |  |  | Pass

## Test Case 3
Test Case ID |  | 3 | Test Case Description | Software inventory and peer-to-peer file sharing tracking
Created By |  | Greg Eure | Reviewed By | Greg Eure |  | Version |  | 1
QA Tester’s Log |  | Test case passed
Tester's Name |  | Greg Eure | Date Tested | 2020-11-21 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data
1 | Access to servers/systems where inventory audit will occur |  |  | 1 | Software Inventory Docucment
2 | Software Inventory Docucment |  |  | 2 | Peer-to-Peer Tracking Document
3 | Peer-to-Peer Tracking Document |  |  | 3
4 |  |  |  | 4
Test Scenario | Verify all inventory tracking data is updated and accurate
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | [INSPECT] Compare Software Inventory with systems to be audited |  | Inventory should contain all software instance license as appropriate | As expected |  |  | Pass
2 | [INSPECT] Compare Peer-to-Peer Tracking inventory with systems to be audited |  | Inventory should contain all peer-to-peer technology mappings as appropriate | As expected |  |  | Pass

## Test Case 4
Test Case ID |  | 4 | Test Case Description | Systems should not display authenticator feedback
Created By |  | Greg Eure | Reviewed By | Greg Eure |  | Version |  | 1
QA Tester’s Log |  | Test case passed
Tester's Name |  | Greg Eure | Date Tested | 2020-11-21 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data
1 | Access to system being tested |  |  | 1 | userid = testuser
2 | MySQL and MySQL Workbench installed |  |  | 2 | password = pAssw0rD
3 | GroupProj database imported |  |  | 3
4 | MySQL server running |  |  | 4
Test Scenario | Verify that password isn't displayed on the screen as it's being typed
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | [TEST] Go to a command shell on the server where MySQL is installed. |  | Command shell should open | As expected |  |  | Pass
2 | [TEST] Enter 'mysql -u testuser -p' |  | Should be prompted for password | As expected |  |  | Pass
3 | [TEST] Enter password |  | password should not be displayed on screen when typed in | As expected |  |  | Pass
4 | [TEST] Open MySQL Workbench |  | MySQL Workbench should open | As expected |  |  | Pass
5 | [TEST] Open or create the connection to the local instance on port 3306 |  | Logon dialog will display | As expected |  |  | Pass
6 | [TEST] Enter user id and password |  | password should not be displayed on screen when typed in | As expected |  |  | Pass

## Test Case 5
Test Case ID |  | 5 | Test Case Description | Allocation of Resources
Created By |  | Greg Eure | Reviewed By | Greg Eure |  | Version |  | 1
QA Tester’s Log |  | Test case not executed
Tester's Name |  | Greg Eure | Date Tested | 2020-11-21 |  | Test Case (Pass/Fail/Not Executed) |  | Not Executed
S # | Prerequisites: |  |  | S # | Test Data
1 | Access to budget and business planning documents |  |  | 1
2 |  |  |  | 2
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario | Review budget and planning documents to ensure compliance with NIST 800-53 item SA-2
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | [INSPECT] Inspect budget and business planning documents and ensure proper resources for information security are allocated. |  | Proper information security resources are allocated | There are no business planning documents |  |  | Not executed

## Test Case 6
Test Case ID |  | 6 | Test Case Description | Denial of Service Protection
Created By |  | Greg Eure | Reviewed By | Greg Eure |  | Version |  | 1
QA Tester’s Log |  | Test case not executed
Tester's Name |  | Greg Eure | Date Tested | 2020-11-21 |  | Test Case (Pass/Fail/Not Executed) |  | Not Executed
S # | Prerequisites: |  |  | S # | Test Data
1 | Access to firewalls and IPS |  |  | 1
2 | Access to network switches and routers |  |  | 2
3 | Access to network monitoring systems |  |  | 3
4 | Database is deployed in a clustered node configuration |  |  | 4
Test Scenario
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | [INSPECT] Look at firewall and IPS to ensure all avaiable DDoS configuration is enabled |  | DDoS configured is enabled | There are no firewall/IPS with DDoS protection |  |  | Not executed
2 | [INSPECT] Look at switches and routers to ensure appropriate access lists are configured |  | ACLs are implemented with approprate rules that mitigate internal/external DDoS attacks | There are no switchs/routers with DDoS protection |  |  | Not executed
3 | [INSPECT] Look at network monitoring to ensure monitoring controls and views are implemented to capture DDoS Alerts, and alerts are being monitored/acknowledged/escalated as appropriate |  | Monitoring alerts are configured and working for DDoS events | There is no network monitoring available |  |  | Not executed
4 | [INSPECT] Confirm the database is deployed on clustered database nodes. |  | Database is deployed in a multi-node configuration | There is no multi-node configuration available |  |  | Not executed

## Test Case 7
Test Case ID |  | 7 | Test Case Description | Malicious Code Protection
Created By |  | Greg Eure | Reviewed By | Greg Eure |  | Version |  | 1
QA Tester’s Log |  | Test case passed
Tester's Name |  | Greg Eure | Date Tested | 2020-11-21 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data
1 | Access to system being tested |  |  | 1 | userid = testuser
2 |  |  |  | 2 | password = pAssw0rD
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario | Verify ClamAV is installed and running and quarantines malicious code
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | [TEST] Go to a command shell on the server where MySQL is installed. |  | Command shell should open | As expected |  |  | Pass
2 | [TEST] tail /var/log/clamav/clamav.log |  | Sun Jun 28 19:08:32 2020 -> Portable Executable support enabled. Sun Jun 28 19:08:32 2020 -> ELF support enabled. Sun Jun 28 19:08:32 2020 -> Mail files support enabled. Sun Jun 28 19:08:32 2020 -> OLE2 support enabled. Sun Jun 28 19:08:32 2020 -> PDF support enabled. Sun Jun 28 19:08:32 2020 -> SWF support enabled. Sun Jun 28 19:08:32 2020 -> HTML support enabled. Sun Jun 28 19:08:32 2020 -> XMLDOCS support enabled. Sun Jun 28 19:08:32 2020 -> HWP3 support enabled. Sun Jun 28 19:08:32 2020 -> Self checking every 3600 seconds. | As expected |  |  | Pass
3 | [TEST] wget www.eicar.org/download/eicar.com |  | 1 file downloaded (eicar.com) | As expected |  |  | Pass
4 | [TEST] ls -l eicar.com |  | no such file or directory | As expected |  |  | Pass
5 | [TEST] sudo ls -l /root/quarantine |  | total 1 eicar.com | As expected |  |  | Pass
6 | [TEST] sudo tail /var/log/clamav/clamonacc.log |  | -------------------------------------- ClamInotif: watching '/home' (and all sub-directories) ClamInotif: watching '/var/www' (and all sub-directories) /home/testuser/eicar.com: Win.Test.EICAR_HDB-1 FOUND /home/testuser/eicar.com: moved to '/root/quarantine/eicar.com' | As expected |  |  | Pass

## Test Case 8
Test Case ID |  | 8 | Test Case Description | Account Management
Created By |  | Muhammad | Reviewed By | Muhammad |  | Version |  | 1
QA Tester’s Log |  | Test Case Passed
Tester's Name |  | Muhammad | Date Tested | 2020-11-21 |  | Test Case (Pass/Fail/Not Executed) |  | pass
S # | Prerequisites: |  |  | S # | Test Data
1 | Accessed mySql through terminal |  |  | 1 | user = ge , pass : MypPassword123
2 | Created a Role with access to GropProj only |  |  | 2 | user = el , pass : MyPassword 321
3 | Created two users 'ge' and 'el' |  |  | 3
4 | Was able to log in and only access that database when logged under those users selecting other database didn't work |  |  | 4
Test Scenario | Given two users access to the database
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Accessed SQL through Terminal |  | Was able to access | As expected |  |  | Pass
2 | Created a Role |  | The role got created | As expected |  |  | Pass
3 | Created users and assigned them the role |  | User created and role assigned | As expected |  |  | Pass
4 | Logged in using one account |  | Was able to log in | As expected |  |  | Pass
5 | Accessed GroupProj |  | Access Given | As expected |  |  | Pass
6 | Tried different database |  | Access Denied | As expected |  |  | Pass

## Test Case 9
Test Case ID |  | 9 | Test Case Description | Separation of Duties
Created By |  | Muhammad | Reviewed By | Muhammad |  | Version |  | 1
QA Tester’s Log |  | Passed
Tester's Name |  | Muhammad | Date Tested | 2020-11-20 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data
1 | Deleted Roles from last test |  |  | 1 | user = ge , pass : MypPassword123
2 | Created New roles |  |  | 2 | user = el , pass : MyPassword 321
3 | Assigned roles |  |  | 3
4 | Test |  |  | 4
Test Scenario | Verify if the duties thar are given are working
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Go to terminal and access SQL under root by mysql-u root -p |  | SQL should open for root | as expected |  |  | Pass
2 | Created two roles by 'create role manager;' & 'create role acessonly;' |  | querry ok and role created | as expected |  |  | Pass
3 | Assigned them to each user by grant role to ----- |  | querry ok and role assigned | as expected |  |  | Pass
4 | Granted manager to EL to manage the whole database GroupProj to manager by "Grant select on GroupProj.* to manager and show databases on *.* to manager" |  | no errors and it added the roles | as expected |  |  | Pass
5 | Granted readonly to ge to read the whole database GroupProj to manager by "Grant connect any database to readonly and Grant select all user securable to readonly" |  | no errors and it added the roles | as expected |  |  | Pass
6 | Tested by logging into mysql -u el -p |  | prompted for password | as expected |  |  | Pass
7 | checked the role 'Select current_role(); |  | should show manager role | as expected |  |  | Pass
8 | Added and deleted a table |  | should add and delete | as expected |  |  | Pass
9 | Tested by logging into mysql -u ge -p |  | prompted for password | as expected |  |  | Pass
10 | checked the role 'Select current_role(); |  | should show readonly role | as expected |  |  | Pass
11 | Tried creating a new table |  | should give an error | as expected |  |  | Pass

## Test Case 10
Test Case ID |  | 10 | Test Case Description | Role-Based Security Training
Created By |  | Muhammad | Reviewed By | Muhammad |  | Version |  | 1
QA Tester’s Log |  | No test case needed
Tester's Name |  | Muhammad | Date Tested | No test |  | Test Case (Pass/Fail/Not Executed) |  | No test case
S # | Prerequisites: |  |  | S # | Test Data
1 | Access To the Policies |  |  | 1
2 | Access to the training material |  |  | 2
3 | Follow the procedures |  |  | 3
4 | Use tools provided |  |  | 4
Test Scenario | Make sure users review the securit training
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
| The user needs to make sure that they reveiw the policies regarding the role |  | Should review the policies so they don't get into issues due to security | As Expected |  |  | No executed
| They should review the training material provided on the security of the role |  | should watch the training videos created for making sure they are secuired with their role | As Expected |  |  | No executed
| They should follow the procedures to do their role set by the companies |  | Don't share the information with other users | As Expected |  |  | No executed
| make sure they are using the tools provided for the security |  | Use Multi Authentication and don't save the password | As Expected |  |  | No executed

## Test Case 11
Test Case ID |  | 11 | Test Case Description | Content of Audit records
Created By |  | Muhammad | Reviewed By | Muhammad |  | Version |  | 1
QA Tester’s Log |  | Audit Records
Tester's Name |  | Muhammad | Date Tested | 2020-11-21 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data
1 | Should have the sql terminal open |  |  | 1 | user = el , pass : MyPassword 321
2 |  |  |  | 2
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
| Go to a command shell on the server where MySQL is installed. |  | Command shell should open | As expected |  |  | Pass
| Enter command 'mysql -u el -p' |  | Should be prompted for password | As expected |  |  | Pass
| Enter command 'set role manager' |  | should change the role | As expected |  |  | Pass
| [TEST] Enter 'use GroupProj;' |  | Database changed' | As expected |  |  | Pass
| Install Audit Log plugin |  | show install the audit plugin | As expected |  |  | Pass
| Restart and should show the audit records |  | Variable_name +-------------------------- ¦ audit_log_buffer_size ¦ audit_log_file ¦ audit_log_flush ¦ audit_log_format ¦ audit_log_handler ¦ audit_log_policy ¦ audit_log_rotate_on_size ¦ audit_log_rotations ¦ audit_log_strategy ¦ audit_log_syslog_facility ¦ audit_log_syslog_ident ¦ audit_log_syslog_priority | As expected |  |  | Pass

## Test Case 12
Test Case ID |  | 12 | Test Case Description | Configuration Settings
Created By |  | Muhammad | Reviewed By | Muhammad |  | Version |  | 1
QA Tester’s Log |  | Moving to a secure hardware
Tester's Name |  | Muhammad | Date Tested | 2020-11-02 |  | Test Case (Pass/Fail/Not Executed) |  | Not executed
S # | Prerequisites: |  |  | S # | Test Data
1 | Running workbench currently on an External Hard drive |  |  | 1
2 |  |  |  | 2
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario | Moving to a secure hardware
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
| Moving it to a more secure os like mac or windows computer |  | Make sure proper security measures are added like microsoft authentication | Not implementing |  |  | Not executed

## Test Case 13
Test Case ID |  | 13 | Test Case Description | Time Stamp
Created By |  | Muhammad | Reviewed By | Muhammad |  | Version |  | 1
QA Tester’s Log |  | Show time stamp
Tester's Name |  | Muhammad | Date Tested | 2020-11-22 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data
1 | Get working SQL Workbench |  |  | 1
2 | Get a table to show time stamp |  |  | 2
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario | Show time stamp
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Created a table group mem |  | Should have group mem info | as expected |  |  | Pass
2 | created groupmemtitle and tied it with groupmem |  | title tied with groupmem | as expected |  |  | Pass
3 | CREATE TABLE groupmemtitle(id INT PRIMARY KEY AUTO_INCREMENT, title varchar (300), content TEXT, publishdate DATETIME, expiredate DATETIME, updated TIMESTAMP default NOW() ON UPDATE NOW(), groupmem_id INT, FOREIGN KEY (groupmem_id) REFERENCES groupmem (id) ON DELETE NO ACTION) ENGINE = INNODB; |  | query went fine | as expected |  |  | Pass
4 | Added data to the table |  | Timestamp should change | as expected |  |  | Pass

## Test Case 14
Test Case ID |  | 14 | Test Case Description | System Use Notification
Created By |  | Muhammad | Reviewed By | Muhammad |  | Version |  | 1
QA Tester’s Log |  | Notifications of database
Tester's Name |  | Muhammad | Date Tested | 2020-11-22 |  | Test Case (Pass/Fail/Not Executed) |  | Not executed
S # | Prerequisites: |  |  | S # | Test Data
1 |  |  |  | 1
2 |  |  |  | 2
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario | Find System notification
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Click Scripting |  | should show the scripting option | as expected |  |  | Pass
| Click scripting shell |  | should open the shell | as expected |  |  | Pass
| Go to Notification |  | should bring all the notification | as expected |  |  | Pass
| You will find all the notification |  | found the notification | as expected |  |  | Pass
| Add a Snipet for notification |  | will show system notification | as expected |  |  | Pass

## Test Case 15
Test Case ID |  | 15 | Test Case Description | Permitted Actions Without Identification or Authentication
Created By |  | Estefania | Reviewed By | Estefania |  | Version |  | 1
QA Tester’s Log |  | Access without authentication or identification
Tester's Name |  | Estefania | Date Tested | 2020-11-22 |  | Test Case (Pass/Fail/Not Executed) |  | pass
S # | Prerequisites: |  |  | S # | Test Data
1 | Open sql terminal |  |  | 1 | /usr/local/mysql/bin/mysql -u root -p
2 | create user with no authentication |  |  | 2 | create user 'noAuth';
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario | Try to access databse witout Authentication
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Try to access the database |  | No database will show, you need authentication to access db | as expected |  |  | Not executed

## Test Case 16
Test Case ID |  | 16 | Test Case Description | Remote Access
Created By |  | Estefania | Reviewed By | Estefania |  | Version |  | 1
QA Tester’s Log |  | Remote Access
Tester's Name |  | Estefania | Date Tested | 2020-11-22 |  | Test Case (Pass/Fail/Not Executed) |  | not executed
S # | Prerequisites: |  |  | S # | Test Data
1 | open sql terminal |  |  | 1 | /usr/local/mysql/bin/mysql -u root -p
2 |  |  |  | 2
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario | Access databse remotely
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | try to access the database remotely |  | since we did not add a remote access feature, we should not be able to connect to the db remotely | as expected |  |  | not executed

## Test Case 17
Test Case ID |  | 17 | Test Case Description | Publicly Accessible Content
Created By |  | Estefania | Reviewed By | Estefania |  | Version |  | 1
QA Tester’s Log |  | Access Public Content
Tester's Name |  | Estefania | Date Tested | 2020-11-22 |  | Test Case (Pass/Fail/Not Executed) |  | pass
S # | Prerequisites: |  |  | S # | Test Data
1 | open sql terminal |  |  | 1 | /usr/local/mysql/bin/mysql -u root -p
2 | Connect to GroupProj database |  |  | 2 | use GroupProj;
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario | Access public content
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Access data from any table (select * from Brazil limit 5;) |  | 5 rows in set (0.01 sec) -public data from Brazil table | as expected |  |  | pass

## Test Case 18
Test Case ID |  | 18 | Test Case Description | System Development Life Cycle
Created By |  | Estefania | Reviewed By | Estefania |  | Version |  | 1
QA Tester’s Log |  | System Development Life Cycle
Tester's Name |  | Estefania | Date Tested | 2020-11-25 |  | Test Case (Pass/Fail/Not Executed) |  | Not executed
S # | Prerequisites: |  |  | S # | Test Data
1 | define roles and responsibliies on database |  |  | 1 | create role database_administrator; create role end_user; create role client; create role testing;
2 |  |  |  | 2
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario | Assess System Development Life Cycle
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | inspect our system development life cycle |  | Some implementation of security roles and resposibilities | As expected |  |  | Not executed

## Test Case 19
|  | 19 | Test Case Description | Incident Handling
Created By |  | Estefania | Reviewed By | Estefania |  | Version |  | 1
QA Tester’s Log |  | Incident Handling
Tester's Name |  | Estefania | Date Tested | 2020-11-23 |  | Test Case (Pass/Fail/Not Executed) |  | not executed
S # | Prerequisites: |  |  | S # | Test Data
1 | open mysql Workbech |  |  | 1
2 |  |  |  | 2
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario | Accessing some Incident handling sources (ex. Server logs)
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | click server on the toolbar |  | report/log options show | as expeceted |  |  | not excuted
2 | click server status |  | administrative server status including CPU load, InnoDB buffer usage, traffic, key efficiency, connections and many more | as expeceted |  |  | not excuted
3 | click server logs |  | server logs are available to show incidents on server | as expeceted |  |  | not excuted
4 | click option files |  | server confiugrations are available to change, including general, advanced and networking | as expeceted |  |  | not excuted

## Test Case 20
Test Case ID |  | 20 | Test Case Description | Boundary Protection
Created By |  | Estefania | Reviewed By | Estefania |  | Version |  | 1
QA Tester’s Log |  | Chech Boundary Protection
Tester's Name |  | Estefania | Date Tested | 2020-11-23 |  | Test Case (Pass/Fail/Not Executed) |  | not executed
S # | Prerequisites: |  |  | S # | Test Data
1 | open sql workbench |  |  | 1
2 |  |  |  | 2
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario | Check Boundary Protection
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | click server in toolbar |  | several server view options | as expected |  |  | not executed
2 | click option files |  | server configurations | as expected |  |  | not executed
| click security |  | boundary security configurations | as expected |  |  | not executed

## Test Case 21
Test Case ID |  | 21 | Test Case Description | Access Enforcement
Created By |  | Estefania | Reviewed By | Estefania |  | Version |  | 1
QA Tester’s Log |  | Access Enforcement
Tester's Name |  | Estefania | Date Tested | 2020-11-23 |  | Test Case (Pass/Fail/Not Executed) |  | pass
S # | Prerequisites: |  |  | S # | Test Data
1 | open sql terminal |  |  | 1 | /usr/local/mysql/bin/mysql -u root -p
2 |  |  |  | 2
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario | Access database as authorized user
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | login as root user |  | access to groupProj database | as expected |  |  | pass
2 | switch to GroupProj database |  | Database changed | as expected |  |  | pass
| select City from Austria; |  | list of city in Austria table | as expected |  |  | pass
| edit table - delete from Austria where City = "Wels"; |  | Query OK, 1 row affected (0.01 sec) | as expected |  |  | pass

## Test Case 22
Test Case ID |  | 22 | Test Case Description | Water Damage Protection
Created By |  | Calvin Ton | Reviewed By | Calvin Ton |  | Version |  | 1
QA Tester’s Log |  | Test case not executed
Tester's Name |  | Calvin Ton | Date Tested | November 23rd, 2020 |  | Test Case (Pass/Fail/Not Executed) |  | Not Executed
S # | Prerequisites: |  |  | S # | Test Data
1 | Access Server Room/Data Center |  |  | 1
2 |  |  |  | 2
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario | Verify that server room is protected from water
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Inspect area and make sure isolation values are employed to shut off water supply |  | Shut off water valves in server rooms, data centers, and mainframe computer rooms | No server room, datacenter, or mainframe computer room to protect from water |  |  | Not Executed

## Test Case 23
Test Case ID |  | 23 | Test Case Description | Plan of Action and Milestones
Created By |  | Calvin Ton | Reviewed By | Calvin Ton |  | Version |  | 1
QA Tester’s Log |  | Test Case not executed
Tester's Name |  | Calvin Ton | Date Tested | Novemeber 24th, 2020 |  | Test Case (Pass/Fail/Not Executed) |  | Not Executed
S # | Prerequisites: |  |  | S # | Test Data
1 | Access to Word Document |  |  | 1
2 |  |  |  | 2
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario | Verify that ogranization has plan of action and milestones to accomplish
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Develop plan of action and milestones for information system to document the organization's planned remedial action to correct weaknesses or deficiencies |  | Proper plans of actions along with milestone for future | No plan of action or milestones were created |  |  | Not executed

## Test Case 24
Test Case ID |  | 24 | Test Case Description | Information System Back up
Created By |  | Calvin | Reviewed By | Calvin |  | Version |  | 1
QA Tester’s Log |  | Test case passed
Tester's Name |  | Calvin | Date Tested | November 23rd, 2020 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data
1 | Download MySQL Workbnech |  |  | 1 | Log into root of LocalHost
2 | Be able to Log into Root |  |  | 2
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario | Verify that data is backed up and stored in a secure location
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Type mysql-workbench into linux terminal |  | MySQL Workbench opens | As expected |  |  | Pass
2 | Create a Schema and Create the tables |  | Schema created along with tables imported with data | As expected |  |  | Pass
3 | Click"Server" Tab |  | Drop down menu opens | As expected |  |  | Pass
4 | Click "Data Export" |  | Brings user to Data Export page to back up data | As expected |  |  | Pass
5 | Select Schema and tables to Back up |  | Schema is Checked and all tables in Schema are "checkmarked" | As expected |  |  | Pass
6 | Click "Start Export" |  | Data Exports into a dump folder | As expected |  |  | Pass

## Test Case 25
Test Case ID |  | 25 | Test Case Description | Information System REcovery and Reconstitution
Created By |  | Calvin | Reviewed By | Calvin |  | Version |  | 1
QA Tester’s Log |  | Test Case Passed
Tester's Name |  | Calvin | Date Tested | November 23rd, 2020 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data
1 | Access to Files |  |  | 1 | Log into root of LocalHost
2 | Access to working MySQL Workbnech |  |  | 2
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario | Verify that data is recovered and is useable
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Type mysql-workbench into linux terminal |  | MySQL Workbench opens | As expected |  |  | Pass
2 | Create Schema ready for data import and refresh tab |  | Created Schema appears on left tab | As expected |  |  | Pass
3 | Click "Server" and then "Data Import" |  | Drop down menu opens and "Data Import" option available. Data Import page opens. | As expected |  |  | Pass
4 | Select elipses after the "Import from Dump Project Folder" and select the correct backup dump folder |  | File application opens and all dump folder options available | As expected |  |  | Pass
5 | Select Imported Schema and make sure all tables are selected |  | Checkmarks are next to Schema and Tables | As expected |  |  | Pass
6 | Click "Start Import" |  | Data Imported into MySQL Workbench as well as mysql in terminal | As expected |  |  | Pass

## Test Case 26
Test Case ID |  | 26 | Test Case Description | Baseline Configuration
Created By |  | Calvin | Reviewed By | Calvin |  | Version |  | 1
QA Tester’s Log |  | Test case attempted
Tester's Name |  | Calvin | Date Tested | November 24th, 2020 |  | Test Case (Pass/Fail/Not Executed) |  | Not Executed
S # | Prerequisites: |  |  | S # | Test Data
1 | Access to Documentation |  |  | 1
2 |  |  |  | 2
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario | Verify that organization has a baseline documentation
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Open a Google Document or Word Document |  | Google Doc opens/Word Document Opens | As expected |  |  | Pass
2 | Document a base setup for the organization's system/data |  | Document Should be filled with base where companh sets up devices and data | There was nothing to document as a baseline |  |  | Not Executed

## Test Case 27
Test Case ID |  | 27 | Test Case Description | Media Access
Created By |  | Calvin | Reviewed By | Calvin |  | Version |  | 1
QA Tester’s Log |  | Test Case Passed
Tester's Name |  | Calvin | Date Tested | November 24th, 2020 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data
1 | Access to Sotraage device i.e Flash Drive |  |  | 1
2 |  |  |  | 2
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario | Verify that external storage device stores data and is secured
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Click "Server" and then click "Data Export" |  | Takes user to Data export page | As expected |  |  | Pass
2 | Select dump folder to store data in and click "Start export" |  | Data should export into a dump folder in the selected directory | As expected |  |  | Pass
3 | Insert Flash Drive/External Hard Drive into Device |  | Device should recognize Flash Drive/External Hard drive | As expeced |  |  | Pass
4 | Copy dump folder over to Flash Drive storage |  | Dump folder should appear in Flash Drive directory | As expected |  |  | Pass
5 | Lock so=torage device with a password |  | Storage should not be able to be accessible unless password is provided | As expected |  |  | Pass

## Test Case 28
Test Case ID |  | 28 | Test Case Description | Visitor Access Records
Created By |  | Calvin | Reviewed By | Calvin |  | Version |  | 1
QA Tester’s Log |  | Test case not executed
Tester's Name |  | Calvin | Date Tested | November 24th, 2020 |  | Test Case (Pass/Fail/Not Executed) |  | Not Executed
S # | Prerequisites: |  |  | S # | Test Data
1 | Access to documentation software |  |  | 1
2 |  |  |  | 2
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario | Verify that visitors and users are being documented when accessing building or data
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Document when users or visitors access data within database |  | Record is recorded | No documentation created as everything done remotely |  |  | Not expected

## Test Case 29
Test Case ID |  | 29 | Test Case Description | Use of external information systems
Created By |  | Junyan | Reviewed By | Junyan |  | Version |  | 1
QA Tester’s Log |  | Test Case Passed
Tester's Name |  | Junyan | Date Tested | November 24th, 2020 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data
1 | Use command line to log into mysql |  |  | 1 | ~$ mysql -u GlobalProj_admin -p
2 |  |  |  | 2
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario | Verify acccess the information system from external information without authorized password will be denied
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Try to access the dtabase as an external information system |  | Access denied due to no authorized password | as expected |  |  | Not executed

## Test Case 30
Test Case ID |  | 30 | Test Case Description | Security Training Records
Created By |  | Junyan | Reviewed By | Junyan |  | Version |  | 1
QA Tester’s Log |  | No test case needed
Tester's Name |  | Junyan | Date Tested | No test |  | Test Case (Pass/Fail/Not Executed) |  | No test case
S # | Prerequisites: |  |  | S # | Test Data
1 | Access to the training documents |  |  | 1
2 | Follow the procedures |  |  | 2
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario | make sure all the training records are documented and monitored
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
| Organization documents and monitors users' security training activities including basic security awareness training and specific security training |  | Training records are documented and monitored | As Expected |  |  | No executed
| Organization retains the training records for a time period based on the security policy |  | Training records are retained in a specific period | As Expected |  |  | No executed

## Test Case 31
Test Case ID |  | 31 | Test Case Description | User Installed Software
Created By |  | Junyan | Reviewed By | Junyan |  | Version |  | 1
QA Tester’s Log |  | Test case passed
Tester's Name |  | Junyan | Date Tested | November 24th, 2020 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data
1 | Software Installation auditing tools |  |  | 1 | Software installation policies
2 | Software installation policies |  |  | 2
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario | User has the ability to install software with necessary privilege; unauthorized installation will trigger system alert
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Establish governing the installation of software by users |  | Users have the ability to install software with necessary privileges | As expected |  |  | Pass
2 | Enforce software installation policies through alarming system |  | alerts should be sent out for unauthorized installations | As expected |  |  | Pass

## Test Case 32
Test Case ID |  | 32 | Test Case Description | Incident Monitoring
Created By |  | Junyan | Reviewed By | Junyan |  | Version |  | 1
QA Tester’s Log |  | Test Case Passed
Tester's Name |  | Junyan | Date Tested | November 24th, 2020 |  | Test Case (Pass/Fail/Not Executed) |  | not executed
S # | Prerequisites: |  |  | S # | Test Data
1 | open MySQL Workbench |  |  | 1 | Servers Log
2 |  |  |  | 2 | Performance reports
3 |  |  |  | 3 | Users info
4 |  |  |  | 4 | Privilege info
Test Scenario | Use MySQL workbench to monitor system incidents
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | click Server on the toolbar |  | Server logs, Performance reports and other options are available | as expeceted |  |  | not excuted
2 | click Server logs |  | Error log files are available to show server errors | as expeceted |  |  | not excuted
3 | click Performance reports |  | Performance reports including memory usage,database schema statistics, wait event times are showing up | as expeceted |  |  | not excuted
4 | click Users and Privileges |  | pysical access like Users and privileges info is available | as expeceted |  |  | not excuted

## Test Case 33
Test Case ID |  | 33 | Test Case Description | Third-Party Personnel Security
Created By |  | Junyan | Reviewed By | Junyan |  | Version |  | 1
QA Tester’s Log |  | Test Case Passed
Tester's Name |  | Junyan | Date Tested | November 24th, 2020 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data
1 | personnel security policies and procedures |  |  | 1 | create role client;
2 | personnel security requirements |  |  | 2 | create user 'GlobalProj_client'@'localhost' identified by 'pA$sw0rD';
3 |  |  |  | 3 | grant client to 'GlobalProj_client'@'localhost';
4 |  |  |  | 4 | grant select on GlobalProj.* to client;
Test Scenario | Third party with authorized role has the ability to log in to the system
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | create role client; create user 'GlobalProj_client'@'localhost' identified by 'pA$sw0rD'; |  | client role is created with password | as expeceted |  |  | pass
2 | grant client to 'GlobalProj_client'@'localhost'; grant select on GlobalProj.* to client; |  | grant client role the access to the database | as expeceted |  |  | pass
3 | third party uses the user name and password to log into the database |  | Third party logs into the database successfully | as expeceted |  |  | pass

## Test Case 34
Test Case ID |  | 34 | Test Case Description | Access Agreements
Created By |  | Junyan | Reviewed By | Junyan |  | Version |  | 1
QA Tester’s Log |  | Test Case Passed
Tester's Name |  | Junyan | Date Tested | November 24th, 2020 |  | Test Case (Pass/Fail/Not Executed) |  | Pass
S # | Prerequisites: |  |  | S # | Test Data
1 | Access Agreements |  |  | 1 | create role end_user;
2 | use command line to create database user |  |  | 2 | create user 'GlobalProj_user'@'localhost' identified by 'pA$sw0rD';
3 |  |  |  | 3 | grant end_user to 'GlobalProj_user'@'localhost';
4 |  |  |  | 4 | grant select, insert, update on GlobalProj.* to end_user;
Test Scenario | User who signed the access agreements has the authorized role and is able to log into the system
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | create role end_user; create user 'GlobalProj_user'@'localhost' identified by 'pA$sw0rD'; |  | user role is created with password | as expeceted |  |  | pass
2 | grant end_user to 'GlobalProj_user'@'localhost'; grant select, insert, update on GlobalProj.* to end_user; |  | grant user role the access to the database | as expeceted |  |  | pass
3 | user uses the user name and password to log into the database |  | user logs into the database successfully | as expeceted |  |  | pass

## Test Case 35
Test Case ID |  | 35 | Test Case Description | Rules of Behavior
Created By |  | Junyan | Reviewed By | Junyan |  | Version |  | 1
QA Tester’s Log |  | Test Case Passed
Tester's Name |  | Junyan | Date Tested | November 24th, 2020 |  | Test Case (Pass/Fail/Not Executed) |  | Not executed
S # | Prerequisites: |  |  | S # | Test Data
1 | Open MySQL workbench |  |  | 1 | User Resource Use
2 |  |  |  | 2 | User behavior statistic data
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario | Use MySQL workbench to monitor user behaviors
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | click Server on the toolbar |  | Performance reports option is available | as expeceted |  |  | not excuted
2 | click Performance reports |  | User Resource Use option is available | as expeceted |  |  | not excuted
3 | click User Resource Use |  | User behaviors statistic data are available | as expeceted |  |  | not excuted

## Test Case 36
Test Case ID |  | 36 | Test Case Description | Fire Protection
Created By |  | Muhammad | Reviewed By | Muhammad |  | Version |  | 1
QA Tester’s Log |  | Test case not executed
Tester's Name |  | Muhammad | Date Tested | 2020-11-25 |  | Test Case (Pass/Fail/Not Executed) |  | Not Executed
S # | Prerequisites: |  |  | S # | Test Data
1 | Access Server Room/Data Center |  |  | 1
2 |  |  |  | 2
3 |  |  |  | 3
4 |  |  |  | 4
Test Scenario | Verify that server room is protected from water
Step # | Step Details |  | Expected Results | Actual Results |  |  | Pass / Fail / Not executed / Suspended
1 | Doesn't Apply to us but if it did we will implement fire hazard detection devices to catch up on incident if anything occur |  | Have fire alarms and smoke alarms in server rooms, data centers, and mainframe computer rooms connected to 911 directly | No server room, datacenter, or mainframe computer room to protect from Fire |  |  | Not Executed